INT2065 小組作業分工（4 人）

課題：一課教 stack、queue、linear linked list（用陣列模擬）

要交：教案、工作紙、可視化工具、10 分鐘簡報 + 5 分鐘問答

簡報材料截止日期：2026 年 11 月 10 日 23:59

中文在前，English follows。

# 分工原則

每人主責一件成品，並主講約 2 至 3 分鐘。

做工具的人技術量最大，所以不寫教案和工作紙全文。

教案、工作紙、工具必須用同一組例子，否則簡報對不上。

個人作業（約 1,500 字訪問反思，12 月 8 日）每人自己做，不計入這份分工。

請在姓名欄填上組員名字。

| 姓名 | 成員 | 主責 | 簡報段落（合共 10 分鐘） |
| --- | --- | --- | --- |
|  | A | 教案 | 學習目標 + 教學法（約 2.5 分鐘） |
|  | B | 工作紙 | 課堂活動 + 工作紙（約 2 分鐘） |
|  | C | 工具 | 人工智能概念 + 系統設計（約 3 分鐘） |
|  | D | 簡報 | 教育價值 + 可行性 + 倫理（約 2.5 分鐘） |

# 一、先一起定死的範圍（全員，第一次會議）

對象：中五或中六，選修 Option C Algorithm and Programming，已懂一維陣列。

一課只比較三種結構如何加入和移除，每種只走一個操作：

Stack：push，學生看 top。

Queue：enqueue，學生看 front 和 rear。

Linear linked list：在指定位置 insert，學生看 head 和 next。

公開試要的是用陣列模擬，不是 Python 的 append / pop，也不是真正的 pointer。pop、dequeue、delete 和學生自己寫完整程式，放到下一課，不放進這份教案。

# 二、成員 A：教案

寫完整教案：課題、對象、先備知識、學習目標、時間分配、教學流程、差異化、評估。

寫教學法依據：用同一張陣列圖比較三者，每種結構只演示一個操作，避免學生混淆 top、front 和 next。

根據成員 C 的說明，把「為何選這個工具」寫進教案。

對照《課程及評估指引》選修 C 的用字：lists, stacks and queues in terms of arrays。

# 三、成員 B：工作紙

學生工作紙只用全員定好的那一組數字。

三題逐步追蹤：push、enqueue、insert。每步要學生寫出陣列和指標。

附教師答案，答案不印給學生。

可加一題課後延伸，但註明不在這節課完成。

題目分量必須是一節課做得到的。

# 四、成員 C：可視化工具

做一個逐步視覺化工具。學生按「下一步」，畫面顯示 top、front、rear 或 next 的改變。

寫一頁系統設計：畫面有什麼、學生怎樣操作、哪一部分用了人工智能。用了就要寫明；如果只是動畫，就不要說成人工智能。

用要點寫出「為何選這個工具」，交給成員 A 放進教案、交給成員 D 放進簡報。

工具裡的數字必須和工作紙相同。

# 五、成員 D：簡報、可行性、倫理

做簡報和講稿，控制全組 10 分鐘，並預留 5 分鐘問答。

寫三段內容：教育價值、可行性、倫理和社會影響。

可行性要面對真實限制：一節課、學校電腦室、工具不必安裝複雜軟件。

倫理要包括：老師核對人工智能產出；學生要用圖解釋答案，不能只抄工具或聊天機械人的結果。可引用教育局 2026 年《人工智能素養學習框架》。

彙整參考資料，以及小組使用人工智能的聲明。

合併最終檔案，提醒全員截止日期。

# 六、交叉檢查

A 檢查 B：工作紙有沒有超出一課範圍。

B 檢查 C：工具例子和工作紙是不是同一組數字。

C 檢查 D：簡報裡的系統描述和真實工具一不一致。

D 檢查 A：教案的學習目標有沒有出現在簡報。

# 七、問答時誰答

課程和學習目標：成員 A。

工作紙題目：成員 B。

工具和系統：成員 C。

可行性、倫理：成員 D。

四人同時在場。被問到自己範圍以外的問題，先接一句，再交給主責的人。

# 八、時間表

9 月 29 日 23:59 前：確認組員名單已交 Google Form。

10 月 6 日前：開第一次會，鎖定例子和工具形式。

10 月 20 日前：教案、工作紙、工具初稿。

11 月 2 日前：簡報、可行性、倫理完成，三份材料已用同一例子。

11 月 8 日：全員彩排 10 + 5 分鐘。

11 月 10 日 23:59：提交簡報材料。

INT2065 Group Project — Division of Work (4 members)

Topic: Teach stack, queue and linear linked list in one lesson (array implementation)

Submit: lesson plan, worksheet, visualisation tool, 10-minute presentation + 5-minute Q&A

Presentation materials due: 10 November 2026, 23:59

# How the work is split

Each member owns one product and speaks for about 2 to 3 minutes.

The tool is the heaviest technical job, so that member does not write the full lesson plan or worksheet.

The lesson plan, worksheet and tool must use the same example, or the presentation will not match.

The individual task (about 1,500 words, interview and reflection, due 8 December) is done by each person alone. It is not part of this split.

Write each member's name in the blank.

| Name | Member | Owns | Presentation slot (10 minutes in total) |
| --- | --- | --- | --- |
|  | A | Lesson plan | Objectives + pedagogy (about 2.5 min) |
|  | B | Worksheet | Lesson activities + worksheet (about 2 min) |
|  | C | Tool | AI concepts + system design (about 3 min) |
|  | D | Slides | Educational value + feasibility + ethics (about 2.5 min) |

# 1. Scope the whole group must lock in the first meeting

Level: S.5 or S.6, Elective Option C Algorithm and Programming, students who already know one-dimensional arrays.

One lesson only compares how the three structures add and remove data. One operation each:

Stack: push. Students watch top.

Queue: enqueue. Students watch front and rear.

Linear linked list: insert at a given position. Students watch head and next.

The public assessment expects an array simulation, not Python append / pop, and not real pointers. pop, dequeue, delete, and students writing full programs belong in the next lesson. Leave them out of this lesson plan.

# 2. Member A — lesson plan

Write the full lesson plan: topic, level, prior knowledge, objectives, timing, procedure, differentiation, assessment.

Write the pedagogical ground: one array diagram is used to compare the three structures, and only one operation is demonstrated for each, so students do not mix up top, front and next.

Using Member C's notes, write "why we chose this tool" into the lesson plan.

Match the wording of the ICT C&A Guide, Elective C: lists, stacks and queues in terms of arrays.

# 3. Member B — worksheet

Use only the example the group agreed.

Three step-by-step traces: push, enqueue, insert. At each step the student writes the array and the pointers.

Provide a teacher answer key. Do not print it for students.

One extension item may be added if it is marked as homework, not as classwork for this lesson.

The worksheet must be finishable in one lesson.

# 4. Member C — visualisation tool

Build a step-by-step visualiser. Each click on "next" shows the change in top, front, rear or next.

Write a one-page system design: what is on screen, what the student does, and which part uses AI. If a part uses AI, say so. If a part is only animation, do not call it AI.

Draft bullet points on why this tool was chosen. Pass them to Member A for the lesson plan and to Member D for the slides.

The numbers in the tool must be the same as the numbers on the worksheet.

# 5. Member D — slides, feasibility, ethics

Build the slide deck and speaker notes. Keep the group to 10 minutes, and leave 5 minutes for questions.

Write three sections: educational value, feasibility, ethical and social implications.

Feasibility must face real limits: one lesson, a school computer room, and no complicated installation.

Ethics must include: the teacher checks any AI output; students explain answers from the diagram and do not copy the tool or a chatbot. The EDB AI Literacy Learning Framework (2026) can be cited.

Compile references and a short statement of how the group used AI.

Merge the final files and remind the group of the deadline.

# 6. Cross-check

A checks B: the worksheet does not go beyond one lesson.

B checks C: the tool uses the same example as the worksheet.

C checks D: the system described on the slides matches the real tool.

D checks A: the lesson objectives appear on the slides.

# 7. Who answers questions

Curriculum and objectives: Member A.

Worksheet items: Member B.

Tool and system: Member C.

Feasibility and ethics: Member D.

All four stay for the Q&A. If a question is outside your part, take it in one sentence, then hand it to the owner.

# 8. Timeline

By 29 September, 23:59: confirm the member list is submitted on the Google Form.

By 6 October: first meeting. Lock the example and the form of the tool.

By 20 October: first drafts of the lesson plan, worksheet and tool.

By 2 November: slides, feasibility and ethics done; all three products use the same example.

8 November: full rehearsal of the 10 + 5 minutes.

10 November, 23:59: submit the presentation materials.